## Slide 1
Manual migration
Sr. No. | Phase | Activity
1 | Inventory Preparation | Create Application Inventory
2 | IDMS Schema Analysis | Detailed analysis of IDMS Record definition
3 | DB2 Database Design & Creation | Develop DB2 database model and Hopex design
4 | Data Migration & sync-up | Modules to Unload data from IDMS and make it compatible for DB2 compare
 |  | Modules to Unload data from DB2 for compare with IDMS unload data
 |  | Modules to compare IDMS & DB2 to identify Delta
 |  | Modules to Update DB2 database to Sync with IDMS
5 | Application Development | Analysis of existing IDMS programs and create Program Specification for new DB2 programs
 |  | Introduced the new application (DEFL) (involved with new DB2 programs) by combined with the existing two applications (involved with IDMS); Develop DB2 programs to replicate IDMS processing; Develop Modules to Compare output from IDMS and DB2 processing.
6 | Unit Testing | Execute IDMS and DB2 process and compare the outputs
7 | GTU Testing (2 month) | Testing by Belfius in GTU environment
 |  | Support by Hexaware for GTU testing
8 | User Acceptance Testing (1 month) | User Acceptance Testing by Belfius
 |  | UAT support by Hexaware
9 | Deployment All environments | Deployment of components for environments
10 | Parallel Run Support (2months) | Parallel executions of IDMS and DB2 process in PROD environment
11 | Decommission | Decommission of IDMS and Removal of switch logic from DB2 programs
Total |  | 

## Slide 2
Phase | Activity | Detail Activity | Deliverable/Output
Inventory Validation |  |  | 
IDMS Schema Analysis | -Analyze Record definition and Set relationship -Significance of fields in our programs | -Analyze Record definition and Set relationship -Data type of Field -Significance of fields in our programs -Checking with business(SME) for validation of the Field | Analysis document for each Record and its fields. Field-Level Mapping Sheet
DB2 Database Design & Creation | -Belfius Architect, added new application into Hopex. -Creation of Database logical diagram in Hopex. -Hopex Admin validation. -DBA create the physical database in DB2. -Request to DBA for indexing and other constraints. | -Discussion with Busines/SME for Tables layout/Column/Keys -House keeping (restart, buffer) tables request directly to DBA, not via Hopex. | Hopex logical diagram Hopex physical db diagram DDL DCLGEN Copybooks
Data Migration & sync-up | Data Extract from IDMS -Data Unload using area sweep. -Make data compatible to DB2 layout for Data comparison | Create custom unload programs and JCL per (or set of) record(s). Testing | Unload JCL and programs for IDMS data . -To create DB2 compatible data
 | Data Unload from DB2 for data comparison | Creation of Unload JCL from DB2 Tables. Testing. | Unload JCL for DB2 Table data
 | Data Comparison and prepare delta feed for DB2 - Data to be deleted from DB2 - Data to be inserted into DB2 - Data to be updated into DB2 | Sort Join of IDMS and DB2 Unload files to identify insert/delete/update. Program to identify updated rows. Testing | Creation of JCL and programs for data comparison
 | Process to update DB2 tables | Creation of JCL and programs to update the DB2 table. Testing(Verify DB2 updates) | Creation of JCL and programs to update the DB2 table
Application Development | Analysis of existing IDMS programs -Creation of PGRSPEC document for DB2 version. -Validation of the solution with Business | Analysis of existing IDMS programs -Creation of PGRSPEC document for DB2 version. -Validation of the solution with Business | PGRSPEC for New DB2 program(s)
 | Clone the new application from existing applications. - Clone the JCL, Programs,Files and Copybooks. - Convert IDMS to DB2 CBL programs. | - Clone (combined) the application newly with new JCLs, Programs, Files,Copybooks. -Creating new DB2 program with restart logic wherever applicable - Replace DB2 program by IDMS programs. | New (DEFL) application DB2 programs JCLs Files Copybooks
Unit Testing | -Preparation of Test Plan -Testing -Comparison of IDMS vs DB2 test results | -Preparation of Test Plan -Testing -Comparison of IDMS vs DB2 test results | Test Plan Test results

## Slide 3
ENTERPRISE TRANSFORMATION ROADMAP
CA–IDMS to IBM Db2 End-to-End Process Flow
Sequential execution stages, cross-functional hand-offs, technical activities, and core deliverables
1
ANALYSIS
Schema & Inventory
⚙ CORE ACTIVITIES
•
Extract IDMS record schemas, subschemas & CALC keys.
•
Map owner-member set pointer linkages.
•
SME workshops to validate field significance & business rules.
•
Analysis on occurs & REDEFINES.
▣ KEY OUTPUTS
▣
Field Mapping Sheet (STM)
▣
Record Specs & Analysis
→ Sent to Hopex Team
›
2
MODELING
Db2 Design & DDL
⚙ CORE ACTIVITIES
•
Using Field mapping sheet Logical class Diagram was created
•
This Logical Class Diagram was then Validated with Hopex Team (HOPEX ADMIN VALIDATION).
•
After Validation DBA team Creates Physical DB2 Tables Using Logical Class Diagram
▣ KEY OUTPUTS
♣
Hopex Physical Data Model
▤
DB2 Table DDL Scripts
</>
DCLGEN Copybooks
→ Feeds Unload & Dev
›
3
CONVERSION
Migration & Sync
⚙ CORE ACTIVITIES
•
Unload full data from IDMS Records.
•
Unload full data from DB2 Tables..
•
Sort-join comparator identifies diffs.
•
Generate row Insert, Update & Delete feeds.
•
Execute delta loaders to keep Db2 in sync by delete, updating and inserting records.
▣ KEY OUTPUTS
>_
Custom Unload Programs
⟳
Syncup Report
✓
100% Recon Reports
→ Keeps Data Synchronized
›
4
DEVELOPMENT
App Modernization
⚙ CORE ACTIVITIES
•
Write Program specification doc's (PGRSPEC).
•
Implement Parallel call to DB2 Pgm's in IDMS code.
•
Write new COBOL with embedded EXEC SQL.
•
Replace DML sweeps with SQL cursors.
•
Add commit frequency & restart logic.
▣ KEY OUTPUTS
▣
New Db2 Programs and JCL's
¥
Program Specification Documents
▤
Db2 Programs & Bind JCL
→ Ready for Parallel Runs
›
5
VERIFICATION
Parallel Run & Cutover
⚙ CORE ACTIVITIES
•
Dual-run identical batch workloads.
•
Parelle Run of IDMS and DB2.
•
Automated bit-by-bit comparison of outputs.
•
Validate performance & concurrency.
•
Obtain business sign-off for cutover.
▣ KEY OUTPUTS
▣
Parallel Test Log
▥
Discrepancy Logs (0 Diff)
▣
Business Cutover Sign-off
→ Production Decommission